## Task Tracker
Person A — Data & Backend — Patient Risk Intelligence Sprint (Jun 25 – Jul 9, 2026)
Date | Day | Task | Category | Status | Notes
2026-06-25 | Thu | TimescaleDB + Postgres containers up, schemas created. Start connector_base.py ABC. | Infra | Done | Stores up: TimescaleDB :5433, Postgres :5434 (5432 taken locally), Qdrant :6333. Schemas verified. connector_base.py ABC done.
2026-06-26 | Fri | Run Synthea (fixed SYNTHEA_SEED), build loader script, populate vitals/labs/meds tables. Write demo_patient_aliases.json. Hand Person B a STUB server. | Data | Done | Synthea loader (seed=42, v4.0.0 jar, 31 patients). demo_patient_aliases.json. Day-1 vitals_trends STUB at :8001/mcp — contract frozen for Person B. Superseded by DB-backed server Jun 29.
2026-06-29 | Mon | Build vitals_trends server: get_vitals_trend, compute_news2_score, list_abnormal_vitals. | MCP Server | Done | Real DB-backed server: sql_connector.py (asyncpg, read-only guard), news2.py (NHS NEWS2), tools.py query live TimescaleDB + FHIR-shape. Same contract as stub. Verified vs demo patient. Built a day early (Jun 28).
2026-06-30 | Tue | Build labs_diagnoses server: get_lab_trend, get_active_diagnoses, get_diagnosis_history. | MCP Server | Done | DB-backed labs_diagnoses: get_lab_trend (FHIR Observation, test_name filter), get_active_diagnoses + get_diagnosis_history (FHIR Condition). Reuses SQLConnector. RBAC: case-manager denied. Verified vs demo-patient-1.
2026-07-01 | Wed | Build medications_interactions server: get_active_medications, check_drug_interactions, get_polypharmacy_risk. | MCP Server | Done | DB-backed medications_interactions: get_active_medications (FHIR MedicationStatement, deduped), check_drug_interactions (curated RxNorm rule set in interaction_rules, illustrative), get_polypharmacy_risk (5+ distinct = elevated). Physician-only RBAC. Verified: lisinopril+naproxen interaction fires for demo-patient-1.
2026-07-02 | Thu | Add RBAC, audit (+purpose_of_access enum), egress guard, cache to all 3 servers built so far. | Hardening | Done | Fixed Core on all 4 servers: auth.py (JWT + scope/group RBAC), audit.py (purpose_of_access enum), egress_guard.py (locked_connector_for), cache.py (@cached 30s), FixedCoreGuard middleware. 401 without token (AUTH_ALLOW_ANONYMOUS for POC).
2026-07-03 | Fri | RBAC pytest matrix (3 roles x 9 tools). CHECKPOINT — flag to the team if behind. | Testing | Done | test_rbac_matrix.py (11 auth-engine unit tests) + test_rbac_matrix_http.py (4×3 HTTP matrix via FixedCoreGuard, 401/403/200). 62 pytest passing.
2026-07-06 | Mon | Qdrant up. Build vector_connector.py and clinical_notes_search (semantic_search_notes, get_recent_notes, get_notes_by_type with note_type/author_role). Pin embedding model to match loader exactly. | MCP Server | Done | vector_connector.py (AsyncQdrantClient, assert_model_matches). clinical_notes_search :8004 — semantic_search_notes, get_recent_notes, get_notes_by_type (note_type/author_role in payload). Embeddings via backend/shared/embeddings.py. RBAC: physician + case-manager allow; nurse deny.
2026-07-07 | Tue | Self-healing on all 4 servers. Rehearse the chaos demo (kill a DB mid-call). | Reliability | Done | self_healing.py + tenacity retries on SQLConnector/VectorConnector (pool/client reset). test_self_healing.py chaos demo: simulated stale pool → retry → success.
2026-07-08 | Wed | MCP Inspector pass on all 4 servers. Re-verify full RBAC matrix (4 servers x 3 roles, ~13 tools). | Testing | Done | docker-compose.yml unified. test_mcp_inspector.py + scripts/mcp_inspector_smoke.py (4/4 tools/list). Full 4×3 RBAC re-verified at HTTP layer.
2026-07-09 | Thu | Final fixes. Live demo support. | Demo | Not started | Final fixes. Live demo support.
Progress (synced to repo Jun 28, 2026)
Tasks Done: |  | Done count
Total Tasks: | 11 | Total tasks | Partial count
% Complete:

## Gap Fixes You Own
Gap Fixes — Items Added During the Audit
Gap | Fix | File(s) | Status
Doctor notes vs. other note types were conflated | Add note_type + author_role fields; get_notes_by_type tool | infra/synthea/load_patients.py (payload), backend/servers/clinical_notes_search/tools.py | Done
Embedding model not pinned — load/query mismatch risk | Pin sentence-transformers/all-MiniLM-L6-v2 in both loader and connector | backend/shared/embeddings.py (single source); loader + vector_connector import it | Done
No deterministic Synthea seed — demo patient not reproducible | Fixed SYNTHEA_SEED + generated demo_patient_aliases.json | infra/synthea/load_patients.py, demo_patient_aliases.json | Done
purpose_of_access was unconstrained free text | Fixed 5-value enum, validated in audit.py | backend/shared/audit.py | Done
Stale 'MinIO' reference in self-heal table (this platform never uses MinIO) | PRD PDF §7.9 MinIO reference — platform uses Qdrant only (confirmed in code/docs; PDF edit out of sprint scope) | Patient_Risk_Intelligence_PRD.docx Section 7.9 | Deferred
Synthea jar was moving tag — patients drifted across machines | Pin SYNTHEA_VERSION=v4.0.0; clear output/ before each load | infra/synthea/load_patients.py | Done
Drug interaction demo had no reference rules | seed-interaction-rules.sql (6 RxNorm pairs, e.g. lisinopril+naproxen on demo-patient-1) | infra/postgres/seed-interaction-rules.sql | Done
Per-server ScopeGuard duplicated Layer-2 logic | Shared FixedCoreGuard + auth.py engine across all 4 servers | backend/shared/middleware.py, backend/shared/auth.py | Done

## Contract Reference
Integration Contract — Read-Only Reference
Item | Value | Notes
Token claims | sub, oid, groups[], scp | scp is space-separated scopes
vitals_trends scope | mcp.vitals.read | Tools: get_vitals_trend, compute_news2_score, list_abnormal_vitals
labs_diagnoses scope | mcp.labs.read | Tools: get_lab_trend, get_active_diagnoses, get_diagnosis_history
medications_interactions scope | mcp.meds.read | Tools: get_active_medications, check_drug_interactions, get_polypharmacy_risk
clinical_notes_search scope | mcp.notes.read | Tools: semantic_search_notes, get_recent_notes, get_notes_by_type
RBAC — clinical-viewer | Allow vitals, labs · Deny meds, notes | —
RBAC — physician | Allow all 4 | —
RBAC — case-manager | Deny vitals, labs, meds · Allow notes | —
purpose_of_access enum | deterioration_review, medication_reconciliation, discharge_planning, care_coordination, routine_review | routine_review is default
Denial response shape | {"error":{"code":"forbidden","reason":"missing scope <scope>"}} | HTTP 403
Embedding model | sentence-transformers/all-MiniLM-L6-v2 | Must match exactly between loader and query
Server ports (direct MCP) | 8001 vitals · 8002 labs · 8003 meds · 8004 notes | Host-run; Kong via host.docker.internal
Tool count | 12 tools (3 per server) | RBAC enforced at server gate (scope + groups[])
No token (production) | HTTP 401 | POC bypass: AUTH_ALLOW_ANONYMOUS=true
Group denial | {"error":{"code":"forbidden","reason":"role not permitted..."}} | HTTP 403 when groups[] disallowed
JWT signature verify | AUTH_VERIFY_SIGNATURE=true (when Keycloak scp wired) | Off by default until Person B mappers live
Self-healing | SELF_HEAL_MAX_ATTEMPTS=3; tenacity on connectors | backend/shared/self_healing.py
Unified compose | docker compose up -d | docker-compose.yml merges data + platform (Jul 8)
Demo patient alias | demo-patient-1 → 080b069b-5108-46b6-ecef-6aacd3b9ef3f | infra/synthea/demo_patient_aliases.json (v4.0.0 / seed 42)
RBAC HTTP matrix tests | test_rbac_matrix_http.py (4×3) + test_mcp_inspector.py | Jul 3/8 acceptance — 62 pytest passing