## Task Tracker
Person B — Platform & Agent — Patient Risk Intelligence Sprint (Jun 25 – Jul 9, 2026)
Date | Day | Task | Category | Status | Notes
2026-06-25 | Thu | Keycloak up (3 roles). Kong up. docker-compose.platform.yml skeleton. | Infra | Not started
2026-06-26 | Fri | Wire Kong<->Keycloak token validation. Stand up registry-db (12 tables). Receive Person A's stub server — start building against it. | Platform | Not started | Person A stub LIVE — MCP Streamable HTTP at http://localhost:8001/mcp (Kong route /mcp/clinical/vitals-trends/dev). Tools: get_vitals_trend, compute_news2_score, list_abnormal_vitals. Scope mcp.vitals.read. Returns FHIR Observation; 403 envelope on missing scope; no-token allowed for now.
2026-06-29 | Mon | Build Onboarding Agent: discover -> suggest -> draft RBAC -> assemble blueprint (against the stub schema). | Agent | Not started
2026-06-30 | Tue | Build Runtime Agent skeleton: Host + Client code, against the stub server. | Agent | Not started
2026-07-01 | Wed | Integrate Runtime Agent with real vitals_trends + labs_diagnoses. | Agent | Not started
2026-07-02 | Thu | Integrate medications_interactions; finalize 3-source fusion logic with citations. | Agent | Not started
2026-07-03 | Fri | CopilotKit chat wired to agent + NextAuth.js login against Keycloak. OTel/Jaeger across 3 servers. CHECKPOINT. | Frontend | Not started
2026-07-06 | Mon | Tremor dashboard skeleton (KPIs, registry status, RBAC breakdown). Add non-anonymous token check to registry-api. | Frontend | Not started
2026-07-07 | Tue | Integrate 4th MCP Client (clinical_notes_search) if Person A shipped it; finalize citation-based answer synthesis. | Agent | Not started
2026-07-08 | Wed | Rate-limit (429) and expired-token (401) demo configs in Kong. Record a full backup demo video. | Demo Prep | Not started
2026-07-09 | Thu | Final fixes. Live demo support. | Demo | Not started
Progress
Tasks Done:
Total Tasks:
% Complete:

## Gap Fixes You Own
Gap Fixes — Items Added During the Audit
Gap | Fix | File(s) | Status
No documented way for a user's token to reach the Runtime Agent | NextAuth.js with Keycloak as OIDC provider; token forwarded as Bearer header | frontend/app/api/auth/[...nextauth]/route.ts | Not started
registry-api had zero access control | Require a valid, non-anonymous Keycloak token on every request | backend/registry/auth.py | Not started
purpose_of_access was unconstrained free text | Chat UI reason-for-query selector offers the fixed 5-value enum | frontend/app/chat/page.tsx | Not started
Doctor notes vs. other note types were conflated | Runtime Agent must pass note_type through when citing clinical_notes_search results | agent/runtime_agent.py, agent/prompts.py | Not started

## Contract Reference
Integration Contract — Read-Only Reference
Item | Value | Notes
Token claims | sub, oid, groups[], scp | scp is space-separated scopes
vitals_trends scope | mcp.vitals.read | Tools: get_vitals_trend, compute_news2_score, list_abnormal_vitals
labs_diagnoses scope | mcp.labs.read | Tools: get_lab_trend, get_active_diagnoses, get_diagnosis_history
medications_interactions scope | mcp.meds.read | Tools: get_active_medications, check_drug_interactions, get_polypharmacy_risk
clinical_notes_search scope | mcp.notes.read | Tools: semantic_search_notes, get_recent_notes, get_notes_by_type
RBAC — clinical-viewer | Allow vitals, labs · Deny meds, notes | —
RBAC — physician | Allow all 4 | —
RBAC — case-manager | Deny vitals, labs, meds · Allow notes | —
purpose_of_access enum | deterioration_review, medication_reconciliation, discharge_planning, care_coordination, routine_review | routine_review is default
Denial response shape | {"error":{"code":"forbidden","reason":"missing scope <scope>"}} | HTTP 403 — render `reason` directly in chat UI
Day-1 stub server | Hardcoded JSON, real tool names, real Kong route | Owed by Person A end of day Jun 26